## Gantt Chart
GANTT CHART
PROJECT TITLE |  | AI Virtual Mouse ¦ Gesture Recognition ¦ Voice Assistant |  |  | COMPANY NAME | [6 empty] | Husler
PROJECT MANAGER |  | Deepak sir |  |  | DATE | [6 empty] | 2021-11-23
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[5 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | SPRINT BACKLOG 1
1.1 | Neutral Gesture | BS+AJ+DS | 2021-11-29 | 0% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Move Cursor | BS+AJ+DS | 2021-12-03 | 0% | bar: WEEK 2 W
1.2 | Left,Right & Double Click | BS+AJ+DS | 2021-12-09 | 0% | bar: WEEK 2 W to WEEK 3 W
1.3 | Drag and Drop | BS+AJ+DS | 2021-12-11 | 0% | bar: WEEK 2 R to WEEK 3 R
2 | SPRINT BACKLOG 2
2.1 | Multiple Item Selection | BS+AJ+DS | 2021-12-12 | 0% | bar: WEEK 4 M to WEEK 4 R
2.2 | Volume and Brightness Control | BS+AJ+DS | 2021-12-15 | 0% | bar: WEEK 4 F to WEEK 5 F
2.3 | Zoom In/Zoom out Functionalities | BS+AJ+DS | 2021-12-20 | 0%
2.4 | AI Assistence(Proton) | BS+AJ+DS | 2021-12-24 | 0%
3 | SPRINT BACKLOG 3
3.1 | Launch/Stop Gesture Recognition | BS+AJ+DS | 2022-02-01 | 0%
3.2 | Google Search on Proton | BS+AJ+DS | 2022-02-03 | 0%
3.2.1 | Find a Location on Google Maps using Proton | BS+AJ+DS | 2022-02-05 | 0%
3.2.2 | File Navigation using Proton | BS+AJ+DS | 2022-02-07 | 0%
3.3 | Current Date using Proton | BS+AJ+DS | 2022-01-09 | 0%
4 | SPRINT BACKLOG 4
4.1 | Current Time using Proton | BS+AJ+DS | 2022-02-13 | 0%
4.2 | Copy/Paste using Proton | BS+AJ+DS | 2022-02-16 | 0%
4.3 | Sleep/Wake up Proton | BS+AJ+DS | 2022-02-20 | 0%
4.4 | Exit | BS+AJ+DS | 2022-02-26 | 0%