## ProductBacklog
PRODUCT BACKLOG
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | User | Use the Neutral Gesture For No Action | I Can halt/stop execution of current gesture | 1 | BS
1 | SB1/US2 | User | Use the V Shape Hand Gesture to Moving around the Computer Window | I Can moves the cursor to the desired location. | 1 | AJ
1 | SB1/US3 | User | Use the Index Finger to Perform Left Button Click | I Can perform single left click functionality | 1 | DS
1 | SB1/US4 | User | Use the Middle Finger to Perform Right Button Click | I Can perform single right click functionality | 1 | BS
1 | SB1/US5 | User | Use the Index and Middle Finger to Perform Double Button Click | I Can perform double click functionality | 1 | AJ
1 | SB1/US6 | User | Use the Pinch (Index + Thumb) Action to Perform Scroll up Function | I Can move and control the webpage horizontaly | 1 | DS
1 | SB1/US7 | User | Use the Pinch (Index + Thumb) Action to Perform Scroll Down Function | I Can move and control the webpage vertically | 1 | BS
1 | SB1/US8 | User | Use the Fist Action and then V Shape Finger to Perform Drag and Drop Function | I Can move/tranfer files from one directory to another | 1 | AJ
2 | SB2/US9 | User | Use the Fist Action to Perform Multiple Item Selection Function | I Can select multiple items to move/transfer desired location | 1 | DS
2 | SB2/US10 | User | Use the Pinch (Index + Thumb) Action to Perform Volume Control Function | I Can change volume dynamically according to the distance move from start point | 1 | BS
2 | SB2/US11 | User | Use the Index Finger and Palm to control music | I Can play/pause the music | 1 | AJ
2 | SB2/US12 | User | Use the Pinch (Index + Thumb) Action to Perform Brightness Control Function | I Can change brightness dynamically according to the distance move from start point | 1 | DS
2 | SB2/US13 | User | Use the L Shape Hand Gesture to Perform Zoom Function | I Can zoom in and zoom out the screen | 1 | BS
2 | SB2/US14 | User | Use the Fist Action from both hands to Perform Screenshort Function | I Can take screen short using hand gesture | 1 | AJ
2 | SB2/US15 | User | Use Voice Assistant (Proton) | I Can interpret human voice to control system | 1 | DS
2 | SB2/US16 | User | Use Proton to Launch Hand Gesture Recognition | I Can turns on webcam for hand gesture recognition. | 1 | BS
3 | SB3/US17 | User | Use Proton to Stop Hand Gesture Recognition | I Can turns off webcam for hand gesture recognition. | 1 | AJ
3 | SB3/US18 | User | Use Proton to Google Search | I Can search given text on Google | 1 | DS
3 | SB3/US19 | User | Use Proton to Find a Location on Google Maps | I Can search user asked location on Google Map | 1 | BS
3 | SB3/US20 | User | Use Proton to Launch Virtual Keyboard | I Can interprets to an screen input method in devices with no physical keyboard | 1 | AJ
3 | SB3/US21 | User | Use Proton to File Navigation | I Can list all the files which are present in Current Directory | 2 | DS
3 | SB3/US22 | User | Use Proton to open Specific File | I Can open the user asked file in current directory | 2 | BS
3 | SB3/US23 | User | Use Proton to go back from Current Directory | I Can Change the Current Directory to Parent Directory and lists the files. | 2 | AJ
3 | SB3/US24 | User | Use Proton to see Current Date | I Can see the current date | 2 | DS
4 | SB4/US25 | User | Use Proton to see Current Time | I Can see the current time | 2 | BS
4 | SB4/US26 | User | Use Proton to Open Window Application | I Can launch that application on windows | 2 | AJ
4 | SB4/US27 | User | Use Proton to Copy & Paste | I Can copies the selected text and then paste | 2 | DS
4 | SB4/US28 | User | Use Proton to Sleep Voice Assistant | I Can pause voice command execution till the assistant is woken up | 2 | BS
4 | SB4/US29 | User | Use Proton to Wake Up Voice Assistant | I Can resumes voice command execution from sleep | 2 | AJ
4 | SB4/US30 | User | Use Proton to Exit | I Can terminates the voice assistant | 2 | DS
Pastes the copied text.Pastes the copied text.

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 | As a User I want to Use the Neutral Gesture For No Action so that I Can halt/stop execution of current gesture. | SB1/US1/T1 | Study of OpenCv Library | BS+AJ+DS | Not Started
|  | SB1/US1/T2 | Set webcam frame width and height | BS | Not Started
|  | SB1/US1/T3 | Implement VideoCapture function from cv2 to open webcam | AJ | Not Started
|  | SB1/US1/T4 | Testing of the module on localmachine. | DS | Not Started
SB1/US2 | As a User I want to Use the V Shape Hand Gesture to Moving around the Computer Window so that I Can moves the cursor to the desired location. | SB1/US2/T5 | Study of Pynput and Pyautogui Library | BS+AJ+DS | Not Started
|  | SB1/US2/T6 | Adjust Index and Middle Finger to V Shape | BS | Not Started
|  | SB1/US2/T7 | Implement moveTo function to desired location | AJ | Not Started
|  | SB1/US2/T8 | Testing of the module on localmachine. | DS | Not Started
SB1/US3 | As a User I want to Use the Index Finger to Perform Left Button Click so that I Can perform single left click functionality | SB1/US3/T9 | Study of Pynput and Pyautogui Library | BS+AJ+DS | Not Started
|  | SB1/US3/T10 | Bend the Index Finger tip toward the palm | BS | Not Started
|  | SB1/US3/T11 | Implement click function with parameter as left | AJ | Not Started
|  | SB1/US3/T12 | Testing of the module on localmachine. | DS | Not Started
SB1/US4 | As a User I want to Use the Middle Finger to Perform Right Button Click so that I Can perform single right click functionality. | SB1/US4/T13 | Study of Pynput and Pyautogui Library | BS+AJ+DS | Not Started
|  | SB1/US4/T14 | Bend the Middle Finger tip toward the palm | BS | Not Started
|  | SB1/US4/T15 | Implement click function with parameter as right | AJ | Not Started
|  | SB1/US4/T16 | Testing of the module on localmachine. | DS | Not Started
SB1/US5 | As a User I want to Use the Index and Middle Finger to Perform Double Button Click so that I Can perform double click functionality. | SB1/US5/T17 | Study of Pynput and Pyautogui Library | BS+AJ+DS | Not Started
|  | SB1/US5/T18 | Join the Index and Middle Finger | BS | Not Started
|  | SB1/US5/T19 | Implement doubleClick function | AJ | Not Started
|  | SB1/US5/T20 | Testing of the module on localmachine. | DS | Not Started
SB1/US6 | As a User I want to Use the Pinch (Index + Thumb) Action to Perform Scroll up Function so that I Can move and control the webpage horizontaly | SB1/US6/T21 | Study of Pynput and Pyautogui Library | BS+AJ+DS | Not Started
|  | SB1/US6/T22 | Use Pinch (Index + Thumb Finger) Action to perform scroll up | BS | Not Started
|  | SB1/US6/T23 | Implement scroll function to scrolling horizontaly | AJ | Not Started
|  | SB1/US6/T24 | Testing of the module on localmachine. | DS | Not Started
SB1/US7 | As a User I want to Use the Pinch (Index + Thumb) Action to Perform Scroll Down Function so that I Can move and control the webpage vertically. | SB1/US7/T25 | Study of Pynput and Pyautogui Library | BS+AJ+DS | Not Started
|  | SB1/US7/T26 | Do Pinch (Index + Thumb Finger) Action to perform scroll down | BS | Not Started
|  | SB1/US7/T27 | Implement scroll function to scrolling vertically | AJ | Not Started
|  | SB1/US7/T28 | Testing of the module on localmachine. | DS | Not Started
SB1/US8 | As a User I want to Use the Fist Action and then V Shape Finger to Perform Drag and Drop Function so that I Can move/tranfer files from one directory to another. | SB1/US8/T29 | Study of Pynput and Pyautogui Library | BS+AJ+DS | Not Started
|  | SB1/US8/T30 | Do Fist and then V Shape Finger Action to perform drag and drop function | BS | Not Started
|  | SB1/US8/T31 | Implement moveTo, copy and paste function | AJ | Not Started
|  | SB1/US8/T32 | Testing of the module on localmachine. | DS | Not Started

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2021-11-29 | 32 |  | Tasks
2021-12-03 | 26
2021-12-09 | 22
2021-12-11 | 0
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
SB2/US9 | As a User I want to Use the Fist Action to Perform Multiple Item Selection Function so that I Can select multiple items to move/transfer desired location. | SB2/US9/T33 | Study of Pynput and Pyautogui Library | BS+AJ+DS | Not Started
|  | SB2/US9/T34 | Do Fist Action to perform multiple item selection function | BS | Not Started
|  | SB2/US9/T35 | Implement keyUp and keyDown function | AJ | Not Started
|  | SB2/US9/T36 | Testing of the module on localmachine. | DS | Not Started
SB2/US10 | As a User I want to Use the Pinch (Index + Thumb) Action to Perform Volume Control Function so that I Can change volume dynamically according to the distance move from start point | SB2/US10/T37 | Study of Pycaw Library | BS+AJ+DS | Not Started
|  | SB2/US10/T38 | Do Pinch (Index + Thumb Finger) Action to control volume | BS | Not Started
|  | SB2/US10/T39 | Implement get_dist, changesystemvolume function | AJ | Not Started
|  | SB2/US10/T40 | Testing of the module on localmachine. | DS | Not Started
SB2/US11 | As a User I want to Use the Index Finger and Palm to control music so that I Can play/pause the music. | SB2/US11/T41 | Study of Pynput and Pyautogui Library | BS+AJ+DS | Not Started
|  | SB2/US11/T42 | Bend the Index Finger tip toward the palm | BS | Not Started
|  | SB2/US11/T43 | Implement click function with parameter as left | AJ | Not Started
|  | SB2/US11/T44 | Testing of the module on localmachine. | DS | Not Started
SB2/US12 | As a User I want to Use the Pinch (Index + Thumb) Action to Perform Brightness Control Function so that I Can change brightness dynamically according to the distance move from start point | SB2/US12/T45 | Study Screen Brightness Control library | BS+AJ+DS | Not Started
|  | SB2/US12/T46 | Do Pinch (Index + Thumb Finger) Action to control volume | BS | Not Started
|  | SB2/US12/T47 | Implement get_dist, get_brightness, fade_brightness function | AJ | Not Started
|  | SB2/US12/T48 | Testing of the module on localmachine. | DS | Not Started
SB2/US13 | As a User I want to Use the L Shape Hand Gesture to Perform Zoom Function so that I Can zoom in and zoom out the screen. | SB2/US13/T49 | Study OpenCV and Mediapipe Library | BS+AJ+DS | Not Started
|  | SB2/US13/T50 | Make L Shape Gesture in Both Hands | BS | Not Started
|  | SB2/US13/T51 | Implement zoomIn and zoomOut function | AJ | Not Started
|  | SB2/US13/T52 | Testing of the module on localmachine. | DS | Not Started
SB2/US14 | As a User I want to Use the Fist Action from both hands to Perform Screenshort Function so that I Can take screen short using hand gesture. | SB2/US14/T53 | Study of Pynput and Pyautogui Library | BS+AJ+DS | Not Started
|  | SB2/US14/T54 | Make Fist Action from Both the hands | BS | Not Started
|  | SB2/US14/T55 | Implement screenshort() function | AJ | Not Started
|  | SB2/US14/T56 | Testing of the module on localmachine. | DS | Not Started
SB2/US15 | As a User I want to Use Voice Assistant (Proton) so that I Can interpret human voice to control system | SB2/US15/T57 | Study of GUI, Pyttsx3, Speech_recognition, wikipedia Library | BS+AJ+DS | Not Started
|  | SB2/US15/T58 | Implementation of GUI | BS | Not Started
|  | SB2/US15/T59 | Implement User Input Field for Commands to Proton | AJ | Not Started
|  | SB2/US15/T60 | Implement Search Button for execute the command | DS | Not Started
|  | SB2/US15/T61 | Testing of the GUI on localmachine. | BS | Not Started
SB2/US16 | As a User I want to using Use Proton to Launch Hand Gesture Recognition so that I Can turns on webcam for hand gesture recognition. | SB2/US16/T62 | Study of OpenCv, Pyttsx3, Speech_recognition, wikipedia Libraries | BS+AJ+DS | Not Started
|  | SB2/US16/T63 | Give command "Proton Launch Gesture Recognition" to turns on webcam for hand gesture recognition | DS | Not Started
|  | SB2/US16/T64 | Testing of the webcam for hand gesture recognition ON on localmachine. | AJ | Not Started

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2021-12-12 | 31 |  | Tasks
2021-12-15 | 28
2021-12-20 | 20
2021-12-24 | 10
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>
SB3/US17 | As a User I want to Use Proton to Stop Hand Gesture Recognition so that I Can turns off webcam for hand gesture recognition. | SB3/US17/T65 | Study of Pyttsx3, Speech_recognition, wikipedia Libraries | BS+AJ+DS | Not Started
|  | SB3/US17/T66 | Give command "Proton Stop Gesture Recognition" to turns off webcam for hand gesture recognition | BS | Not Started
|  | SB3/US17/T67 | Testing of the webcam for hand gesture recognition OFF on localmachine. | AJ | Not Started
SB3/US18 | As a User I want to Use Proton to Google Search so that I Can search given text on Google | SB3/US18/T68 | Study of Pyttsx3, Speech_recognition, wikipedia Libraries | DS | Not Started
|  | SB3/US18/T69 | Give command "Proton Search {text_you_wish_to_search}" to Search on Google | BS+AJ+DS | Not Started
|  | SB3/US18/T70 | Implement get, open, url, split, record_audio function | BS | Not Started
|  | SB3/US18/T71 | Testing of the Google Search on localmachine. | DS | Not Started
SB3/US19 | As a User I want to Use Proton to Find a Location on Google Maps so that I Can search user asked location on Google Map | SB3/US19/T72 | Study of Pyttsx3, Speech_recognition, eel Libraries | BS+AJ+DS | Not Started
|  | SB3/US19/T73 | Give command "Proton Find a location {location_you_wish_to_find}" to Search on Google Maps | BS | Not Started
|  | SB3/US19/T74 | Implement get, open, record_audio, addUserMsg function | AJ | Not Started
|  | SB3/US19/T75 | Testing of the Google Maps on localmachine. | DS | Not Started
SB3/US20 | As a User I want to Use Proton to Launch Virtual Keyboard so that I Can interprets to an screen input method in devices with no physical keyboard. | SB3/US20/T76 | Study of OpenCV, Pynput Libraries | BS+AJ+DS | Not Started
|  | SB3/US20/T77 | Give command "Proton Open Virtual Keyboard" to open a virtual keyboard | BS | Not Started
|  | SB3/US20/T78 | Implement Controller, rectangle, putText, press function | AJ | Not Started
|  | SB3/US20/T79 | Testing of the Virtual Keyboard on localmachine. | BS+AJ+DS | Not Started
SB3/US21 | As a User I want Use Proton to File Navigation so that I Can list all the files which are present in Current Directory. | SB3/US21/T77 | Study of os, app libraries | BS | Not Started
|  | SB3/US21/T78 | Give command "Proton list files / Proton list" to open a list of all the files in current directories | AJ | Not Started
|  | SB3/US21/T79 | Implement listdir, addAppMsg function | DS | Not Started
|  | SB3/US21/T80 | Testing of the File Navigation on localmachine. | BS | Not Started
SB3/US22 | As a User I want Use Proton to open Specific File so that I Can open the user asked file in current directory | SB3/US22/T81 | Study of os, app libraries | AJ | Not Started
|  | SB3/US22/T82 | Give command "Proton open {file_number}" to open the user asked file in current directory | DS | Not Started
|  | SB3/US22/T83 | Implement join, isFile, start, listdir, addAppMsg function | BS+AJ+DS | Not Started
|  | SB3/US22/T84 | Testing of the Open Specific File on localmachine. | AJ | Not Started
SB3/US23 | As a User I want to Use Proton to go back from Current Directory so that I Can Change the Current Directory to Parent Directory and lists the files. | SB3/US23/T85 | Study of os, app libraries | DS | Not Started
|  | SB3/US23/T86 | Give command "Proton go back / Proton back" to change from current directory to parent directory | BS+AJ+DS | Not Started
|  | SB3/US23/T87 | Implement join, listdir, addAppMsg function | BS | Not Started
|  | SB3/US23/T88 | Testing of the go back file functionality on localmachine. | AJ | Not Started
SB3/US24 | As a User I want to Use Proton to see Current Date so that I Can see the current date. | SB3/US24/T89 | Study of os, app, datetime libraries | DS | Not Started
|  | SB3/US24/T90 | Give command "Proton what is today's date / Proton date" to see current date | BS+AJ+DS | Not Started
|  | SB3/US24/T91 | Implement strftime, split function | BS | Not Started
|  | SB3/US24/T92 | Testing of the current date functionality on localmachine. | AJ | Not Started

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2022-02-01 | 34 |  | Tasks
2022-02-03 | 30
2022-02-05 | 25
2022-02-07 | 20
2022-01-09 | 15
2022-02-12 | 5
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>
SB4/US25 | As a User I want to Use Proton to see Current Time so that I Can see the current time. | SB4/US25/T93 | Study of os, app libraries | BS+AJ+DS | Not Started
|  | SB4/US25/T94 | Give command "Proton what is the time / Proton time" to see current time | AJ | Not Started
|  | SB4/US25/T95 | Implement now, split function | BS | Not Started
|  | SB4/US25/T96 | Testing of the current time functionality on localmachine. | AJ | Not Started
SB4/US26 | As a User I want to Use Proton to Open Window Application so that I Can launch that application on windows. | SB4/US26/T97 | Study of os, app libraries | DS | Not Started
|  | SB4/US26/T98 | Give command "Proton Open {window_application}" to launch a window application | BS+AJ+DS | Not Started
|  | SB4/US26/T99 | Implement system, startfile function | AJ | Not Started
|  | SB4/US26/T100 | Testing of the open window application on localmachine. | DS | Not Started
SB4/US27 | As a User I want to Use Proton to Copy & Paste so that I Can copies the selected text and then paste. | SB4/US27/T101 | Study of os, app, pynput libraries | BS+AJ+DS | Not Started
|  | SB4/US27/T102 | Give command "Proton Copy / Paste" to copy and paste selected text | BS | Not Started
|  | SB4/US27/T103 | Implement pressed, press, release function | BS+AJ+DS | Not Started
|  | SB4/US27/T104 | Testing of the Copy & Paste Functionality on localmachine. | BS | Not Started
SB4/US28 | As a User I want to Use Proton to Sleep Voice Assistant so that I Can pause voice command execution till the assistant is woken up. | SB4/US28/T105 | Study of os, app, pynput libraries | DS | Not Started
|  | SB4/US28/T106 | Give command "Proton Bye" to Sleep / Pause the voice assistant | BS+AJ+DS | Not Started
|  | SB4/US28/T107 | Implement sleep function | BS | Not Started
|  | SB4/US28/T108 | Testing of the Sleep Voice Assistant Functionality on localmachine. | BS+AJ+DS | Not Started
SB4/US29 | As a User I want to Use Proton to Wake Up Voice Assistant so that I Can resumes voice command execution from sleep | SB4/US29/T109 | Study of os, app, pynput libraries | BS | Not Started
|  | SB4/US29/T110 | Give command "Proton Wake Up" to resume the voice assistant | AJ | Not Started
|  | SB4/US29/T111 | Implement is_awake, wish function | BS+AJ+DS | Not Started
|  | SB4/US29/T112 | Testing of the Resume Voice Assistant Functionality on localmachine. | BS | Not Started
SB4/US30 | As a User I want to Use Proton to Exit so that I Can terminates the voice assistant | SB4/US30/T113 | Study of os, app, pynput libraries | AJ | Not Started
|  | SB4/US30/T114 | Give command "Proton Exit" to terminates the voice assistant | DS | Not Started
|  | SB4/US30/T115 | Implement close, exit function | BS | Not Started
|  | SB4/US30/T116 | Testing of the Terminate Voice Assistant Functionality on localmachine | BS+AJ+DS | Not Started

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2022-02-13 | 47 |  | Tasks
2022-02-16 | 40
2022-02-20 | 30
2022-02-26 | 0
Days